GOVERNANÇA BRASIL (GOVBR) — VBU

Document shareable with leadership  •  Effective: 26/Jun/2026 → 26/Sep/2026

# 90-Day Transformation Plan

Four commitments. Named blockers. Measurable outcomes.

VBU: Governança Brasil (GOVBR)

Leader: Henrique Barreto

Portfolio: Volaris

Created: 26/Jun/2026

90-day review: 26/Sep/2026

# Transformation hypothesis (North Star)

The VBU’s “+$1 per customer/month” hides in two places at once: (1) contractual readjustment above the inflation index, justified by the value of new satellites delivered to the star base, and (2) cloud-COGS reduction via the legacy-product rewrite, which expands per-customer margin. Capturing it by Day 90 means restructuring the product (COGS-rewrite + satellites as a single program) and redistributing the build cadence beyond a single R&D leadership — proving, on the star municipalities that renew in September, that an adopted satellite becomes an above-index readjustment.

Cluster A — 18 star clients: Viamão · Santa Maria · Itabira · São Sebastião/SP · Montes Claros · Uruguaiana · Porto Feliz · São Roque · Ananindeua · Leme · Contagem · Olinda · Boituva · Rolândia · Eldorado do Sul · Saquarema · Pato Branco · Ubá

# Commitment 1 — BUILD (ship + how you ship)

Grid movement: Build is already Green on capability (strong Builder 360; first agent in 2 days). 90-day move: from “Green tied to one leadership cadence” → “Green in production, adopted and scalable”.

What’s changing: Decide the agentic architecture (single layer vs. per-module agents, across 64 modules / 35M lines); map the base’s expectations via a Cluster A discovery and ship the first prioritized wave of satellites; start the rewrite with the highest cloud-cost modules — operating Builder 360 well beyond a single leadership cadence.

The measurable:

Agentic architecture approved in writing — week 3

Cluster A discovery prioritizing the satellite roadmap — week 2–3

≥15 satellites live and adopted by 10–20 of the 18 star municipalities (active use) — week 10

≥5/64 modules (highest cloud cost) rewritten with −30% cloud measured on the bill — week 12

20 people certified on Builder 360 (incl. the 10 PS technicians) — week 6

Timeline and owner: 90 days → 26/Sep. Owner: Ivan Filagrana, with Higo Mariano.

First blocker / unlock: The bottleneck is not capacity — there are 70+ devs. It is the cadence (pace) that R&D leadership imposes. Unlock: an architecture decision that parallelizes + 20 certified on Builder 360 distributing build authority, reducing dependence on a single leadership’s pace.

# Commitment 2 — SELL (find, win, keep)

Grid movement: Sell is Red today (weakest row). 90-day move: Red → Surviving/Succeeding, proving above-index readjustment on the September renewals + retention of the rest.

What’s changing: Convert satellite adoption into above-IPCA readjustment on the star municipalities that renew in the window where the product already exists (September); defend at IPCA (retention, no upsell) those renewing earlier; use the agents’ governance/audit dossier as the formal price justification.

The measurable:

Upsell (IPCA + 5–10%) on the ~6 September renewals: Viamão (PM), Saquarema (CM), Boituva (PM), Porto Feliz (PM+CM), Rolândia (PM)

Defend at full IPCA (retention) the Jul–Aug and overdue renewals: Olinda, Itabira, Ananindeua (CM), Leme, Eldorado do Sul (PM), Saquarema (PM), São Roque (PM+CM)

Pricing-unlocking Responsible AI: audit-trail standard + “non-delegable act always human” published as a renewal argument — by week 8

Timeline and owner: Tied to the renewal calendar (renewals cannot be brought forward). Owner: Miguel Júnior + regional directors: Rodrigo Braga (MG/RJ), Roberlei Fernandes (SP), Rodrigo (RS), João Macedo (PR), Tomás (North-Northeast).

First blocker / unlock: Public client questions above-index readjustment without proof of value → unlock = proven satellite adoption (Build’s metric) becomes the contractual justification. Structural market constraint: contract deadlines are immovable and new sales take up to 3 years — within 90 days the upside is only the September renewals; new sales are seeded, not closed.

Note: Attrition (7.7% → 3.5%; ~3% political/integrity, ~4.7% addressable) is an annual metric and partly already “baked in” — moved to Beyond 90 days.

# Commitment 3 — UPSIDES > BLOCKERS (opportunity > friction)

Grid movement: The most volatile row (“people will be problems”) → “self-teaching product + PS building + decentralized R&D cadence”. Friction converted into throughput.

What’s changing: Builder 360 starts generating each feature with an embedded PS kit (video/manual) + Mia documentation, so that scaling satellites does not scale support linearly; 10 PS technicians gain autonomy to build features on Builder 360, redistributing the cadence beyond a single leadership; Mia is trained on the documented satellites.

The measurable:

10 PS technicians building on Builder 360 (subset of the 20 certified, not additive) — week 3

100% of satellites delivered with embedded PS kit + Mia documentation

Mia trained on the satellites’ documentation; ticket deflection-% = 6-month outcome (depends on the product existing)

Timeline and owner: PS-builders week 3. Owners: Tiago Nogueira (PS), Manuela Bolsonaro + Lívia Sá (Mia/Customer Care), Higo Mariano (Builder 360 enablement).

First blocker / unlock: Change the cadence/pace imposed by R&D leadership. Unlock: redefine the decision cadence and align leadership’s long-term goals with decentralization and the development of technical leaders — an incentive mechanism, not an informal conversation. Risk to watch: clients used to human service — do not push self-service beyond cultural absorption.

# Commitment 4 — 2× THE BUSINESS (credible path forward)

Grid movement: 2× is Red today. 90-day move: not to double, but to prove the path to 2× in 3 years is real, de-risking the product-restructuring engine.

What’s changing: Treat COGS-rewrite + satellite creation as ONE product-restructuring program. The dev team invests in product improvement (cloud↓ and satellites↑) while PS covers emergency demand. Builder 360 becomes a shareable group capability (Equiplano uses it to generate revenue in the other company — not a sale).

The measurable:

5/64 modules with −30% cloud measured → extrapolated model showing the path to −60% and margin expansion

Proven stickiness = the ~6 above-index September readjustments (stitched to Commitment 2)

3-year business case with the two 90-day proof points validated — presented to the portfolio

Timeline and owner: 90 days → 26/Sep. Owner: Henrique Barreto, with Ivan/Higo on product proof.

First blocker / unlock: Product risk — rewrite/satellites not ready in time. Unlock: architecture decision in week 3 + attack the 5 highest-cloud modules first + scope the readjustment only to the September renewals.

# Three pre-named risks

| Risk | Early signal I’m watching for |
| --- | --- |
| PS compression — services revenue at risk / field capacity overrun by the satellites | Spike in in-person training demand PS cannot meet; visit/ticket backlog rising after each satellite |
| Code audit gap — technical debt in the 35M lines stalls the rewrite | Rewrite velocity on the 5 modules below plan; cloud bill not dropping in the modeled proportion |
| Competitor wedge — “silver bullet for everyone” (signal: Kleber/Denardi/useall) | A competitor announcing an agentic/AI layer for municipalities before us |

# Accountability

Portfolio/Group Leader (Volaris): ______________________

Review 30 days: 26/Jul/2026  •  60 days: 26/Aug/2026  •  90 days: 26/Sep/2026

Cohort peer in contact: ______________________

Weekly ritual (Friday, 30 min): KRs on the real dashboard, exceptions, trust-ladder promotion decisions, new risks.

# Beyond 90 days

At 6 months (≈ Dec/2026): rewrite advancing toward −60% cloud; Mia deflection relieving N1; 2nd wave of satellites; first validation of the “compliance / 10%” thesis.

At 12 months: mature rewrite (low disruption desktop→new); addressable attrition 7.7% → 3.5%; above-index readjustment consolidated; Builder 360 with no single cadence bottleneck.

Path to 2× in 3 years: margin via COGS-cloud + recurring above-index revenue + new satellite/compliance line + long-cycle new sales (up to 3 years) seeded now + Builder 360 as a shared group capability.

# The leader’s three lines

Most confident to deliver: BUILD — Builder 360 ready; architecture + 5 modules + 20 certified within reach.

Most likely to underdeliver: SELL (above-index readjustment) — hostage to product timing against an immovable renewal calendar.

Stop doing: letting the R&D cadence be dictated by a single leadership — decentralizing the pace makes room for the whole plan.